## Road Map
SEO ROADMAP - Unnifidata
Activities | Description | Ownership | Month 1 (Nov) | Month 2 (Dec) | Month 3 (Jan) | Month 4 (Feb) | Month 5 (Mar) | Month 6 (Apr)
Monthy SEO Audit | Analyze SEO health and share the audit report by every month (With Recomendations) | Asquare
SEO monthly reporting | Create SEO monthly report (which includes Traffic, Keywords & website performance)with comparison of competitors and share the report by every month | Asquare
Blog topics recommendation | Suggest blogs topic to target the high perfomance keywords | Asquare
Link Monitoring | Monitoring backlinks that are pointing to domain and look for spam and optimize. | Asquare
Monthly GSC checkup | Analyze website health check in Google Search Console and share the report by every month | Asquare
Keyword Research & Analysis
Keywords research | Finding untapped keywords | Asquare
Keyword Gap Analysis | Analyze competitors keywords which we are not in rank | Asquare
| And Finalize the keywords, which having high potential | Asquare
Social Profiles - creation
GMB
Facebook
Instagram
LinkedIn
YouTube
Content Creation
Blogs on website |  | Asquare |  | 4 per month | 4 per month | 4 per month | 4 per month | 4 per month
Service Pages |  | Asquare & Unnifi Data
Social Media posts |  | Asquare | 6 per month | 12 per month | 12 per month | 12 per month | 12 per month | 12 per month
One Monthly Creative for Ads
On-Page Optimization - existing pages & Upcoming blogs & service pages
Internal Duplication | Creation of unique content with 2% targeted keyword density for identical pages. | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Titles | Remove duplicate titles and will add new titles with finalized keywords | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
| Optimize new titles with finalized keywords in the missing title tags | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Meta Descriptions | Remove duplicate description and will add unique content with 160 characters | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
| Add new content (with 160 characters)in the missing description | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Image & Alt-Text Used | Optimize all missing alt text for the images | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Heading Tags | Optimize the header tags the pages does not have ( H1, H2, H3) | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Headers Duplication | Optimize duplicate Headers with proper heading tags ( H1, H2, H3) | Asquare | Existing Pages | New Pages | New Pages | New Pages | New Pages | New Pages
Technical SEO
Regular Update of Robots.txt | Check and update robots.txt file for crawling and indexing the website | Asquare
Regular Update of Sitemap | Update sitemap when new pages are uploaded and submit to the GSC | Asquare
Site structure analysis and URL restructure | Restructure the URLs | Asquare
Internal Errors | Configure internal errors (404, 403,505) | Asquare
Internal linking | Optimize internal link to inter connect all pages in the website | Asquare
Canonicalization | Optimize the rel canonical tag for missing canonicalization pages | Asquare
Website Speed | Optimize website's mobile and desktop version to improve load time. | Asquare
Schema Mark up | Implementation of schema markup on all pages in the website | Asquare
Mobile-friendly optimization | Optimize site for mobile. Check via google mobile friendly test. | Asquare
Off page
Backlink Audit and Clean up | Audit the spam backlinks and disavow links through Search console | Asquare
Competitor link analysis | Analyze competitors backlinks | Asquare
Web Directories & Blog Directories submissions | Submit blogs created to various blog directories and popular niche web directories. | Asquare
Company Directory Submissions | Just like general web directories, you can submit your site to general company directories. | Asquare
Q&A Sites Submissions | Sites like Quora can build a few nofollow links that can also send you traffic, by mentioning your website as a source in your answer. | Asquare
Local SEO | GMB / Audit Local citations | Asquare